## Planning prévisionnel (v1)
Task	Charge / (jours)	24.04.17	25.04.17	26.04.17	27.04.17	28.04.17	01.05.17	02.05.17	03.05.17	04.05.17	05.05.17	08.05.17	09.05.17	10.05.17	11.05.17	12.05.17	15.05.17	16.05.17	17.05.17	18.05.17	19.05.17	22.05.17	23.05.17	24.05.17	25.05.17
Profile page: Info from a specific user	1
Friends page: Friendship request sending form	0.5
Send friendship request	0.5
Refuse friendship request	0.5
Accept friendship request	2
Friends page: List of friends	0.5
Cancel friendship request	1
Remove someone from friends list	1.5
Post creation	0.5
Post display	1.5
Profile page: Posts from a specific user	1
Post deletion	0.5
Post update	1
Comment creation	1
Comment display	1
Comment deletion	0.5
Comment update	1
Reaction addition	0.5
Reaction deletion	0.5
Homepage: Posts (+ comments, reactions) from self & friends	4
Settings: App settings, to display and to change	2
Task	Charge / (jours)
Profile page: Info from a specific user	1
Friends page: Friendship request sending form	0.5
Send friendship request	0.5
Refuse friendship request	0.5
Accept friendship request	2
Friends page: List of friends	0.5
Cancel friendship request	1
Remove someone from friends list	1.5
Post creation	0.5
Post display	1.5
Profile page: Posts from a specific user	1
Post deletion	0.5
Post update	1
Comment creation	1
Comment display	1
Comment deletion	0.5
Comment update	1
Reaction addition	0.5
Reaction deletion	0.5
Homepage: Posts (+ comments, reactions) from self & friends	4
Settings: App settings, to display and to change	2

## Planning prévisionnel (v2)
Task	Charge / (jours)	Front/Back	24.04.17	25.04.17	26.04.17	27.04.17	28.04.17	01.05.17	02.05.17	03.05.17	04.05.17	05.05.17	08.05.17	09.05.17	10.05.17	11.05.17	12.05.17	15.05.17	16.05.17	17.05.17	18.05.17	19.05.17	22.05.17	23.05.17	24.05.17	25.05.17
Create app base: Codebase + Database	0.5	Both	x																									Légende		Joseph
Profile page: Info from a specific user	1	Front		x																										Brendan
	1	Back		x																										Both
Friends page: Friendship request sending form	0.5	Front		x
Friends page: List of friends	0.5	Front			x
	0.5	Back			x
Post creation	0.5	Front				x
	0.5	Back			x
Post display	1	Front					x
	0.5	Back						x	x	x	x
Post deletion	0.5	Front					x
	0.5	Back				x	x
Comment creation	0.5	Front										x	x	x
	1.5	Back										x	x
Comment display	0.5	Front						x	x	x	x
	0.5	Back
Comment deletion	0.5	Front												x
	0.5	Back												x
Reaction addition	0.5	Front												x
	1	Back												x
Reaction deletion	0.5	Front													x
	1	Back													x
Homepage: Posts (+ comments, reactions) from self & friends	0.5	Front													x
	0.5	Back													x												← Minimal version
Send friendship request	0.5	Front
	1	Back														x	x	x	x	x
Refuse friendship request	0.5	Front
	0.5	Back																					x
Accept friendship request	0.5	Front
	2	Back																			x	x
Cancel friendship request	0.5	Front
	1	Back																					x
Remove someone from friends list	0.5	Front
	1	Back
Post update	1	Front
	0.5	Back
Comment update	0.5	Front
	0.5	Back