## Planning prévisionnel (v1)
Task	Charge / (jours)	24/04/17	25/04/17	26/04/17	27/04/17	28/04/17	01/05/17	02/05/17	03/05/17	04/05/17	05/05/17	08/05/17	09/05/17	10/05/17	11/05/17	12/05/17	15/05/17	16/05/17	17/05/17	18/05/17	19/05/17	22/05/17	23/05/17	24/05/17	25/05/17
Profile page: Info from a specific user	1
Friends page: Friendship request sending form	0,5
Send friendship request	0,5
Refuse friendship request	0,5
Accept friendship request	2
Friends page: List of friends	0,5
Cancel friendship request	1
Remove someone from friends list	1,5
Post creation	0,5
Post display	1,5
Profile page: Posts from a specific user	1
Post deletion	0,5
Post update	1
Comment creation	1
Comment display	1
Comment deletion	0,5
Comment update	1
Reaction addition	0,5
Reaction deletion	0,5
Homepage: Posts (+ comments, reactions) from self & friends	4
Settings: App settings, to display and to change	2
Task	Charge / (jours)
Profile page: Info from a specific user	1
Friends page: Friendship request sending form	0,5
Send friendship request	0,5
Refuse friendship request	0,5
Accept friendship request	2
Friends page: List of friends	0,5
Cancel friendship request	1
Remove someone from friends list	1,5
Post creation	0,5
Post display	1,5
Profile page: Posts from a specific user	1
Post deletion	0,5
Post update	1
Comment creation	1
Comment display	1
Comment deletion	0,5
Comment update	1
Reaction addition	0,5
Reaction deletion	0,5
Homepage: Posts (+ comments, reactions) from self & friends	4
Settings: App settings, to display and to change	2

## Planning prévisionnel (v2)
Task	Charge / (jours)	Front/Back	24/04/17	25/04/17	26/04/17	27/04/17	28/04/17	01/05/17	02/05/17	03/05/17	04/05/17	05/05/17	08/05/17	09/05/17	10/05/17	11/05/17	12/05/17	15/05/17	16/05/17	17/05/17	18/05/17	19/05/17	22/05/17	23/05/17	24/05/17	25/05/17		Légende		Joseph
Create app base: Codebase + Database	0,5	Both																												Brendan
Profile page: Info from a specific user	1	Front																												Joseph (done)
	1	Back																												Brendan (done)
Friends page: Friendship request sending form	0,5	Front																												Both
Friends page: List of friends	0,5	Front																												Both (done)
	0,5	Back
Post creation	0,5	Front
	0,5	Back
Post display	1	Front
	0,5	Back
Post deletion	0,5	Front
	0,5	Back
Comment creation	0,5	Front
	1,5	Back
Comment display	0,5	Front
	0,5	Back
Comment deletion	0,5	Front
	0,5	Back
Reaction addition	0,5	Front
	1	Back
Reaction deletion	0,5	Front
	1	Back
Homepage: Posts (+ comments, reactions) from self & friends	0,5	Front
	0,5	Back																									Minimal version
Send friendship request	0,5	Front
	1	Back
Refuse friendship request	0,5	Front
	0,5	Back
Accept friendship request	0,5	Front
	2	Back
Cancel friendship request	0,5	Front
	1	Back
Remove someone from friends list	0,5	Front
	1	Back
Post update	1	Front
	0,5	Back
Comment update	0,5	Front
	0,5	Back