## Planning prévisionnel (v1)
Task	Charge / (jours)	24/04/17	25/04/17	26/04/17	27/04/17	28/04/17	01/05/17	02/05/17	03/05/17	04/05/17	05/05/17	08/05/17	09/05/17	10/05/17	11/05/17	12/05/17	15/05/17	16/05/17	17/05/17	18/05/17	19/05/17	22/05/17	23/05/17	24/05/17	25/05/17
Profile page: Info from a specific user	1
Friends page: Friendship request sending form	0,5
Send friendship request	0,5
Refuse friendship request	0,5
Accept friendship request	2
Friends page: List of friends	0,5
Cancel friendship request	1
Remove someone from friends list	1,5
Post creation	0,5
Post display	1,5
Profile page: Posts from a specific user	1
Post deletion	0,5
Post update	1
Comment creation	1
Comment display	1
Comment deletion	0,5
Comment update	1
Reaction addition	0,5
Reaction deletion	0,5
Homepage: Posts (+ comments, reactions) from self & friends	4
Settings: App settings, to display and to change	2
Task	Charge / (jours)
Profile page: Info from a specific user	1
Friends page: Friendship request sending form	0,5
Send friendship request	0,5
Refuse friendship request	0,5
Accept friendship request	2
Friends page: List of friends	0,5
Cancel friendship request	1
Remove someone from friends list	1,5
Post creation	0,5
Post display	1,5
Profile page: Posts from a specific user	1
Post deletion	0,5
Post update	1
Comment creation	1
Comment display	1
Comment deletion	0,5
Comment update	1
Reaction addition	0,5
Reaction deletion	0,5
Homepage: Posts (+ comments, reactions) from self & friends	4
Settings: App settings, to display and to change	2

## Planning prévisionnel (v2)
Task	Charge / (jours)	Front/Back	24/04/17	25/04/17	26/04/17	27/04/17	28/04/17	01/05/17	02/05/17	03/05/17	04/05/17	05/05/17	08/05/17	09/05/17	10/05/17	11/05/17	12/05/17	15/05/17	16/05/17	17/05/17	18/05/17	19/05/17	22/05/17	23/05/17	24/05/17	25/05/17		Légende		Joseph
Create app base: Codebase + Database	0,5	Both	x																											Brendan
Profile page: Info from a specific user	1	Front		x																										Joseph (done)
	1	Back		x																										Brendan (done)
Friends page: Friendship request sending form	0,5	Front		x																										Both
Friends page: List of friends	0,5	Front			x																									Both (done)
	0,5	Back			x
Post creation	0,5	Front				x
	0,5	Back			x
Post display	1	Front					x
	0,5	Back									x
Post deletion	0,5	Front					x
	0,5	Back					x
Comment creation	0,5	Front												x
	1,5	Back											x
Comment display	0,5	Front									x
	0,5	Back
Comment deletion	0,5	Front												x
	0,5	Back												x
Reaction addition	0,5	Front												x
	1	Back												x
Reaction deletion	0,5	Front													x
	1	Back													x
Homepage: Posts (+ comments, reactions) from self & friends	0,5	Front													x
	0,5	Back													x												Minimal version
Send friendship request	0,5	Front
	1	Back
Refuse friendship request	0,5	Front
	0,5	Back
Accept friendship request	0,5	Front
	2	Back
Cancel friendship request	0,5	Front
	1	Back
Remove someone from friends list	0,5	Front
	1	Back
Post update	1	Front
	0,5	Back
Comment update	0,5	Front
	0,5	Back